## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Agrasha Patel |  | Gemini API returned 429 RESOURCE_EXHAUSTED due to request rate limits. | Sprint 2 | Agrasha Patel | API / Rate Limit | Reviewed quota limits and planned request consolidation with graceful error handling. | 2026-10-02 | Open | Retry limits and API quota configuration need verification.
2 | Agrasha Patel |  | Inconsistent structured output from the LLM caused evaluation parsing issues. | Sprint 2 | Agrasha Patel | Output Validation | Used Pydantic schemas and structured JSON output validation. | 2026-08-30 | Closed | Structured output validation added.
3 | Agrasha Patel |  | Hallucination detection could produce false positives without sufficient supporting evidence. | Sprint 2 | Agrasha Patel | Evaluation Logic | Refined detection criteria to require specific evidence and reasoning for flagged claims. | 2026-09-08 | Closed | Continue validating against varied examples.
4 | Agrasha Patel |  | Conditional expression used to display Streamlit status messages printed DeltaGenerator output. | Sprint 4 | Agrasha Patel | UI / Display | Replaced conditional expression with explicit if/else Streamlit message calls. |  | Closed | Status messages display correctly after the fix.
5 | Agrasha Patel |  | Batch CSV evaluation could be affected by large input size or API request limits. | Sprint 3 | Agrasha Patel | Performance / API | Added or planned input validation and graceful handling of request-limit errors. |  | Open | Verify current implementation with large CSV files.
6 | Agrasha Patel |  | Missing or invalid Gemini API key prevents evaluation from running. | Sprint 2 | Agrasha Patel | Configuration / Security | Configured the API key through environment variables and documented secure secret handling. | 2026-09-15 | Closed | Verify deployment secrets and never commit .env.
7 | Agrasha Patel |  | PDF report generation may fail if evaluation results contain missing or unexpected fields. | Sprint 4 | Agrasha Patel | Reporting / Data Handling | Validate report inputs and test PDF generation for single and batch evaluation. | 2026-10-01 | Open | Confirm edge-case tests pass.
8 | Agrasha Patel |  | End-to-end evaluation workflow requires regression testing after code changes. | Sprint 4 | Agrasha Patel | Testing | Ran pytest tests/test_m4_end_to_end.py; a previous run reported 8 passed. |  | Closed | Re-run tests before final submission.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others